## Slide 1
2nd General Meeting
10th-12th November 2017
Work Package 2:
Climatic & Agricultural Data
Raül Marcos
Coordinators and developers of BSC tasks
PostDoc Researchers – Nube González –Albert Soret Barcelona Supercomputing Centre, raul.marcos@bsc.es

## Slide 2: Main objectives of WP2
Implementation of bias corrected seasonal predictions
Monthly production of seasonal predictions
Deployment of the operational weather forecast events system (e.g. for extremes)
Production of decadal projections for the 3 different regions considered in the project
Implementation of calibrated models for the prediction of plant phenology and yield.
Implementation of calibrated irrgiation models for the prediction of annual water requirements.

## Slide 3: Gantt Diagram of WP2. What have we done?
2017
2018
2019

## Slide 4: Gantt Diagram of WP2
2017
2018
2019
Milestone 2.2: Availability of seasonal forecast simulations for the diagnostic case of study (BSC)
Deliverable 2.1: Seasonal forecast predictions quality assessment report (BSC)

## Slide 5: Gantt Diagram of WP2
2017
2018
2019
Milestone 2.1: Availability of weather forecast information for the 3 demo-sites (METEOSIM)
Deliverable 2.1: Report on weather forecast extreme events (METEOSIM)

## Slide 6: Gantt Diagram of WP2
2017
2018
2019
Milestone 2.3: Availability of calibrated phenological and irrigation requirement models for the different demo zones and cultivars (IRTA)
Deliverable 2.3: Report on the performance of the phenological model (IRTA)

## Slide 7: Gantt Diagram of WP2
2017
2018
2019
Milestone 2.3: Availability of calibrated phenological and irrigation requirement models for the different demo zones and cultivars (IRTA)
Deliverable 2.4: Report on the performance of irrigation requirements model (IRTA)

## Slide 8: Gantt Diagram of WP2
2017
2018
2019
Milestone 2.4: Real-time seasonal-phenological forecast simulations (BSC, MET, IRTA)

## Slide 9: Gantt Diagram of WP2
2017
2018
2019
Deliverable 2.5: Decadal projection performance report (METEOSIM)

## Slide 10: Gantt Diagram of WP2. What we have to do?
2018
2019
2020
Deliverable 2.6: Report on coordinated seasonal forecast – phenological – irrigation requirement models for real-time applications (BSC)

## Slide 12: Status of BSC tasks
<Insert here
the event name>
Completed
Verification of raw model (ECMWF System 4 and ECMWF System 5) against reanalysis (JRA55)
  Performed globally (monthly / 3-monthly) for Tmax, Tmin, Tmean and precip
    Fair Ranked Probability Skill Score
    Fair Continuous Ranked Probability Skill Score
    Ensemble Mean Correlation
    Reliability diagrams
Verification of raw model (ECMWF System 5) against demo-site observations (Ataide, Raïmat and Mirabella)
  Performed globally (monthly / 3-monthly) for Tmax, Tmin, Tmean and precip
    Fair Ranked Probability Skill Score
    Fair Continuous Ranked Probability Skill Score
    Ensemble Mean Correlation
    Reliability diagrams
1st Technical Meeting

## Slide 13: Status of BSC tasks
<Insert here
the event name>
Completed
Bias correction
  Performed globally (monthly / 3-monthly) for ECMWF System5 and JRA55
    Calibration
    Simple bias correction
Verification of bias-corrected model (ECMWF System 5) against reanalysis (JRA55)
  Performed globally (monthly / 3-monthly) for Tmax, Tmin, Tmean and precip
    Fair Ranked Probability Skill Score
    Fair Continuous Ranked Probability Skill Score
    Ensemble Mean Correlation
    Reliability diagrams
1st Technical Meeting

## Slide 14: Status of BSC tasks
<Insert here
the event name>
Completed
Operational implementation of bias-corrected System 5 forecasts
  Performed globally (monthly / 3-monthly) for ECMWF System5 and JRA55
    Calibrated
    Verified with the Fair Ranked Probability Skill Score
  Performed at each demo-site (monthly basis for tas and prlr)
    Downscaled (calibrated)
    Verified with the Fair Ranked Probability Skill Score
1st Technical Meeting

## Slide 15: Results achieved
1st Technical Meeting
JAS / tas / System 5 – System 4 ens. Mean correalation / Start Date: 1st June / 1981-2015
JAS / tas / System 5 Ens-mean correalation / Start Date: 1st June / 1981-2015

## Slide 16: Results achieved
1st Technical Meeting
JAS / tas / System 5 Ens-mean correalation / Start Date: 1st June / 1981-2015
JAS / prlr / System 5 – System 4 ens. Mean correalation / Start Date: 1st June / 1981-2015

## Slide 17: Results achieved
1st Technical Meeting
JAS / ECMWF System 5/ FRPSS / Start Date: 1st June / 1981-2015
Precipitation
Tas

## Slide 18: Results achieved
1st Technical Meeting
JAS / Calibrated ECMWF System 5 / CFRPSS / Start Date: 1st June / 1981-2015
Precipitation
Tas

## Slide 19: Results achieved
1st Technical Meeting

## Slide 20: Next steps
End of perfect-prognosis analog downscaling application. Verification.
Verification and bias correction of MeteoFrance System 5 and GLOSEA 5 (MetOffice)
Multi-model construction and verification.
<Insert here
the event name>
1st Technical Meeting

## Slide 21
Raül Marcos-Matamoros
raul.marcos@bsc.es
Thank you for you Attention!

## Slide 22
2nd General Meeting
Napoli, 2018 Dec 10th – 12th
TASK 2.2
Operational weather forecast extreme events system
Ignasi Porras
iporras@meteosim.com

## Slide 23: T2.2 – Summary of the task
Main objectives of the task:
  Develop and supply weather forecast services:
    Short-term forecast: up to 48 h.
    Medium-term forecast: up to 240 h.
    Delivery date:
      Month #12 (Jun 2018)
    Main use:
      Minimize risks related to coming weather extreme events.
      Planning short-term and mid-term vineyards activities.
    Task status:
      Short-term operational system [COMPLETED]
      Mid-term operational system [COMPLETED]
      Operational Raimat weather station data. [COMPLETED]
      D2.2. Report on weather forecast extreme events (M12). [COMPLETED]
      Short-term model bias reduction improvement. [ONGOING]
      Update D2.2. (M24). [NOT STARTED]

## Slide 24: T2.2 – Results achieved
5
6
7
8
9
10
11
12
1
2
MAY
JUN
JUL
JAN
FEB
AUG
SEP
OCT
NOV
DEC
3
4
5
2018
2019
MAR
APR
MAY
Short Term Forecast:
  Configuration domains schema for the 3 demo-areas.
  JSON short-term data.
  Operational system.
Mid-Term Forecast:
  GEFS data operational download.
  Post-process -> Fractions of models that falls in each bin.
  JSON mid-term data.
  Operational system.
Raimat weather station:
  Send data operationally to Meteosim’s FTP.
Short-term model bias reduction :
  Best WRF model configuration.
  WRF Data Assimilation System (data from satellites, METAR, RAOB and weather stations)
  Background Error Covariance.
  Update D2.2.

## Slide 25: T2.2 – Short-term obtaining dataset
1st General Meeting
Model data:
  Weather Research & Forecasting (WRF-ARW).
  1km horizontal resolution.
  48h forecasting length.
  2 updates per day: 00 and 12 UTC.
  Deterministic forecasting.
Variables:
  Temperature.
  Precipitation.
  Relative humidity.
  Wind speed.
  Global radiation.

## Slide 26: T2.2 – Results short-term – Raimat fcst

## Slide 27: T2.2 – Results short-term – Mastroberardino fcst

## Slide 28: T2.2 – Results short-term – Symington fcst

## Slide 29: T2.2 – Mid-term obtaining dataset
Model data:
  Global Ensemble Forecasting System (GEFS).
  0,5 deg horizontal resolution.
  240h forecasting length.
  2 updates per day: 00 and 12 UTC.
  Probabilistic forecasting.
Variables:
  Temperature.
  Maximum temperature.
  Minimum temperature.
  Precipitation.
  Relative humidity.
  Wind speed.
  Global radiation.

## Slide 30: T2.2 – Results mid-term
Europe level
Demo-site time series level
MEMBER valid_date T2M RH2M WSPD10M PREC DSWRF LON LAT COMPANY
01 2018120600 10.0 78 2.8 0.0 0 0.50742 41.6625 Codorniu
01 2018120603 9.1 70 3.2 0.0 0 0.50742 41.6625 Codorniu
01 2018120606 8.4 73 3.0 0.0 0 0.50742 41.6625 Codorniu
01 2018120609 10.9 68 3.0 0.0 60 0.50742 41.6625 Codorniu
01 2018120612 15.4 60 5.8 0.0 210 0.50742 41.6625 Codorniu
01 2018120600 6.2 81 0.8 0.0 0 14.9814 41.0615 Mastroberardino
01 2018120603 6.3 77 0.3 0.0 0 14.9814 41.0615 Mastroberardino
01 2018120606 7.0 79 1.2 0.0 0 14.9814 41.0615 Mastroberardino
01 2018120609 11.4 70 2.8 0.0 140 14.9814 41.0615 Mastroberardino
01 2018120612 13.7 57 3.6 0.0 280 14.9814 41.0615 Mastroberardino
01 2018120600 6.7 94 0.5 0.0 0 -7.1091 41.2484 Symington
01 2018120603 6.5 95 0.9 0.0 0 -7.1091 41.2484 Symington
01 2018120606 5.9 96 1.0 0.0 0 -7.1091 41.2484 Symington
01 2018120609 8.8 97 0.8 0.0 30 -7.1091 41.2484 Symington
01 2018120612 14.5 71 1.5 0.0 180 -7.1091 41.2484 Symington

## Slide 31: T2.2 – Next steps
1
2
JAN
FEB
3
4
5
2019
MAR
APR
MAY
Short-term model bias reduction :
  Best WRF model configuration.
  WRF Data Assimilation System (data from satellites, METAR, RAOB and weather stations)
  Background Error Covariance.
  Update D2.2.

## Slide 32
Ignasi Porras
iporras@meteosim.com
Thank you for you Attention!

## Slide 33
Technical Meeting
10th - 12th November 2018, Naples
WP2
Task 2.3 & 2.4
Omar García Tejera
Researcher
omar.garcia@irta.cat
<Insert here
Logo of the organisation>

## Slide 34: Task’s objectives
Task 2.3
  Development and implementation of:
    A model to predict bud break
    A model to predict the different phenological stages (from bloom to veraison)
    A model to predict harvest
    A model to predict the leaf fall
Task 2.4
  Development and implementation of:
    A model to estimate future irrigation needs

## Slide 35: Task’s objectives
Task 2.3
  Development and implementation of
    A model to predict bud break
    A model to predict the different phenological stages (from bloom to veraison)
    A model to predict Harvest
    A model to predict the leaf fall
Task 2.4
  Development and implementation of
    A model to estimate future irrigation needs

## Slide 36: Task’s objectives
Weather Forecasts
(BSC & MeteoSim)
Run
IRTA & UNAP
models
Provide recommendations
to the end users

## Slide 37: Presentation Index
What have we done
Where are we
Future work

## Slide 38: What have we done
First approach.
  Bud Break BRIN (García de Cortazar-Atauri et al, 2009)
  Phenology Berry model (Parker et al, 2011)
  Irrigation VSIM (Williams & Ayars, 2005)

## Slide 39: What have we done
Seasonal weather forecasts
Bud break
and
Phenology model
Temperature
Monthly Basis
Temperature
Daily Basis

## Slide 40: What have we done
Seasonal weather forecasts
Bud break
and
Phenology model
Temperature
Monthly Basis
Temperature
Daily Basis
Data accommodation

## Slide 41: What have we done
VSIM (Irrigation needs)
  Specific to California varieties and conditions
  Unit issues

## Slide 42: What have we done
IRRIGATION NEEDS
Development of a custom irrigation model for VISCA
Notes: Both, the phenological and irrigation models descriptions can be found into the deliverables

## Slide 43: Where are we
Notes: We see that deviation increases as the CF date advance. This will have implications that we will discuss later

## Slide 44: Where are we

## Slide 45: Where are we
Notes: Veraison at beginning of August

## Slide 46: Where are we

## Slide 47: Where are we

## Slide 48: Where are we

## Slide 49: Where are we

## Slide 50: Future Work
Improving Model Response to Crop Forcing

## Slide 51: Future Work
To compare crop coefficients values for Touriga Nacional and Aglianico to tune irrigation needs

## Slide 52
Omar García
omar.garcia@irta.cat
Thank you for you Attention!

## Slide 53
General Meeting
10th - 12th December 2018, Naples
WP2
Task 2.3
Fabrizio Cartenì
Post-doc Researcher
fabrizio.carteni@unina.it
<Insert here
Logo of the organisation>

## Slide 54: Task’s objectives
Task 2.3
  Development and implementation of:
    A model to predict bud break
    A model to predict the different phenological stages (from bloom to veraison)
    A model to predict harvest
    A model to predict the leaf fall

## Slide 55: Presentation Index
What have we done?
Where are we?
Future work

## Slide 56: What have we done?
Development of LEAF model engine

## Slide 57: What have we done?
LEAF MODEL
- Vegetative growth
- Soluble Solids accumulation
- Leaf fall
CLIMATE SERVICE
Sensor Service
- Weather stations data:
  Temperature
  Globar Irradiation
VDI
- Mid-term weather forecast:
  Temperature
  Globar Irradiation
Back-end
- Parcel info
- Achieved:
  Phenology
- Predicted:
  Phenology
  Soil Water Deficit
send predictions
Development of LEAF model (Operational Version)

## Slide 58: Where are we?
LEAF model calibration
1. Mastroberardino - Aglianico
TENUTA RADICI

## Slide 59: Where are we?
LEAF model calibration (2017 - Aglianico - No irrigation)
DOY
Leaves FW [g]
Shoots FW [g]
Fruits FW [g]
Fruits DW [g]
Soluble Solids [brix]
DOY
DOY
Trimming 0%
Trimming 30%
Trimming 60%

## Slide 60: Where are we?
LEAF model calibration
Soluble Solids [brix] at harvest
Same conditions, different observed SS
No water stress treatment
2. Codorniu (2018) - Tempranillo - Chardonnay
3. Symington (2018) - Touriga Nacional
1. Mastroberardino (2017) - Aglianico
Chart: Achieved
| 23.05 | 20.149999999999999 | 21.02 | 21.2
BrixSim | 23.3614 | 23.3614 | 21.9747 | 21.9747
BrixSim | 23.8116 | 24.1493 | 23.7805 | 24.8952 | 24.7082
BrixSim | 23.8237 | 23.8277 | 22.5433 | 20.7895 | 24.4033 | 24.3008 | 24.0317 | 24.4254 | 24.0193 | 20.8091
BrixSim | 22.516 | 22.516 | 22.516 | 22.516
ita | 25.7453 | 26.1114 | 25.4218 | 25.3884 | 25.7851 | 25.4218 | 25.4097 | 26.1114 | 25.045 | 25.3884 | 25.7453 | 25.0312 | 25.7726 | 25.3884 | 25.4097 | 25.7851 | 25.7851 | 25.7726 | 25.0312 | 25.4097 | 26.1114 | 25.7726 | 25.4097 | 25.045 | 25.7851 | 25.7453 | 25.0312 | 25.3884 | 25.0312 | 25.4218 | 25.7453 | 25.4218 | 25.7726 | 25.045 | 25.045 | 26.1114
Crop
Forcing

## Slide 61: Where are we?
LEAF model calibration
Leaf Fall predictions
2. Codorniu (2018) - Tempranillo - Chardonnay
3. Symington (2018) - Touriga Nacional
1. Mastroberardino (2017) - Aglianico
COMPANY | VARIETY | PU_ID | predicted Leaf Fall
Mastroberardino | Aglianico | 37 | 309
Mastroberardino | Aglianico | 43 | 339
Mastroberardino | Aglianico | 45 | 339
Mastroberardino | Aglianico | 51 | 339
Mastroberardino | Aglianico | 52 | 340
Mastroberardino | Aglianico | 53 | 340
Mastroberardino | Aglianico | 56 | 339
Mastroberardino | Aglianico | 61 | 340
Codorniu | Tempranillo | 123 | 319
Codorniu | Tempranillo | 124 | 331
Codorniu | Tempranillo | 125 | 274
Codorniu | Tempranillo | 126 | 331
Codorniu | Tempranillo | 114 | 297
Codorniu | Tempranillo | 115 | 293
Codorniu | Tempranillo | 116 | 295
Codorniu | Tempranillo | 117 | 293
Codorniu | Tempranillo | 128 | 319
Codorniu | Chardonnay | 129 | 263
Codorniu | Chardonnay | 130 | 263
Codorniu | Chardonnay | 131 | 257
Codorniu | Chardonnay | 132 | 257
Symington | TourigaNacional | 310 | 320
Symington | TourigaNacional | 312 | 320
Symington | TourigaNacional | 333 | 320
Symington | TourigaNacional | 334 | 320
…

## Slide 62: Future Work
Refine calibration and validate
Predict harvest date
DOY
Soluble Solids [brix]
Desired Sugar Content
Predicted harvest date

## Slide 63
Fabrizio Cartenì
fabrizio.carteni@unina.it
Thank you for you Attention!

## Slide 64
2nd General Meeting
Napoli, 2018 Dec 10th – 12th
TASK 2.5
Decadal climatic data
Josep Maria Solé Tasias
Climate Analyst
Project Manager
Meteosim, SL · jmsole@meteosim.com

## Slide 65: Summary
OBJECTIVE:
  To deliver the best climate information at multi-decadal scale (30 years)
Delivery date
  Month #24 (Jun 2019)
Characterization:
  Main use: Strategic planning and adaptation decisions for vineyards  Maps.
  Resolution: Fine scale / decadal
Development of the task:
  Obtaining and processing the datasets [COMPLETED]
  Validation of model data [ONGOING]
  Decadal/Seasonal analysis. [NOT STARTED]
  Report [NOT STARTED]
2nd General Meeting

## Slide 66: (1) Obtaining the datasets
Variables:
  Mean temperature.
  Max. daily temperature.
  Min. daily temperature.
  Precipitation.
Model data:
  EURO-CORDEX (EUR-11)
  CMIP5 models, downscaled at 0.11°
  rotated pole grid (≈12.5 km).
  Daily time resolution
  Experiments:
    Evaluation. Period 1989 – 2011.
    Historical. Period 1950 – 2005.
    RCP4.5 (10 members) Period 2006 – 2100
    RCP8.5 (9 members) Period 2006 – 2100
Climate observations:
  E-OBS v16.0 Period 1950 – 2016.
  0.22° rotated pole grid.
  Daily time resolution
2nd General Meeting
GCM1
RCM1
RCM2
RCM3
GCM2
RCM1
RCM2
RCM3
Reanalysis
RCM1
RCM2
RCM2
1950
2005
2100
HISTORICAL
RCP’s
1989
2010
EVALUATION
UNCERTAINTY
CMIP5
…

## Slide 67: (2) Validation
OBJECTIVE:
  To assess whether the models reproduce the current climate  Reliability of projections.
  By comparing the simulations with gridded observations.
Datasets:
  Hindcast (ERA-INTERIM + RCM)  Evaluation of the downscaling method.
  Historical (GCM + RCM) --> Evaluation Global + Downscaling.
Validation exercises:
  EUR: Spatial patterns of seasonal means (climatology).
  EUR: Spatial patterns of seasonal trends
  REG: Annual cycle
  REG: Seasonal trends
  Interannual variability
2nd General Meeting

## Slide 68: (2) Validation
EUR: European level (PRECIPITATION)
  Spatial patterns of seasonal mean
2nd General Meeting
E-OBS
CORDEX-Evaluation (Ens. Mean)

## Slide 69: (2) Validation
EUR: European level (PRECIPITATION)
  Spatial patterns of seasonal mean
2nd General Meeting
E-OBS
CORDEX-Evaluation (Ens. Mean)

## Slide 70: (2) Validation
EUR: European level
  Spatial patterns of seasonal mean
2nd General Meeting
E-OBS
CORDEX-Historical (Ens. Mean)

## Slide 71: (2) Validation
EUR: European level
  Spatial patterns of seasonal mean
2nd General Meeting
E-OBS
CORDEX-Historical (Ens. Mean)

## Slide 72: (2) Validation
EUR: European level
  Spatial patterns of seasonal mean
2nd General Meeting
E-OBS
CORDEX-Evaluation (Ens. Mean)

## Slide 73: (2) Validation
EUR: European level
  Spatial patterns of seasonal mean
2nd General Meeting
E-OBS
CORDEX-Evaluation (Ens. Mean)

## Slide 74: (2) Validation
EUR: European level
  Spatial patterns of seasonal mean
2nd General Meeting
E-OBS
CORDEX-Historical (Ens. Mean)

## Slide 75: (2) Validation
EUR: European level
  Spatial patterns of seasonal mean
2nd General Meeting
E-OBS
CORDEX-Historical (Ens. Mean)

## Slide 76: (2) Validation
REG: Regional level (Annual cycle)
2nd General Meeting

## Slide 77: (2) Validation
REG: Annual cycle - Precipitation - Catalunya
2nd General Meeting

## Slide 78: (2) Validation
REG: Annual cycle - Precipitation - Porto
2nd General Meeting

## Slide 79: (2) Validation
REG: Annual cycle - Precipitation - Napoli
2nd General Meeting

## Slide 80: (2) Validation
REG: Annual cycle – Temperature - Catalonia
2nd General Meeting

## Slide 81: (2) Validation
REG: Regional level – Temperature - Porto
2nd General Meeting

## Slide 82: (2) Validation
REG: Regional level – Temperature - Napoli
2nd General Meeting

## Slide 83: (3) Decadal analysis
Decadal values
  Projected climate minus baseline.
  Trends
1970 | 1980 | 1990 | 2000 | 2010 | 2020 | 2030 | 2040 | 2050 | 2060
1970 - 2000 |  |  |  | 2005 – 2035 (2020) |  |  |  |  | 
1970 - 2000 |  |  |  |  | 2015 – 2045 (2030) |  |  |  | 
1970 - 2000 |  |  |  |  |  | 2025 – 2055 (2040) |  |  | 
2nd General Meeting

## Slide 84: Next steps
Climate indices
2nd General Meeting

## Slide 85
Josep Maria Solé Tasias
jmsole@meteosim.com
Thank you for you Attention!